## Diary
Diploma thesis diary: |  |  |  | 5BHET
Rudolf Migirov |  |  |  | 2019/20
|  | Time worked: | 279 | Invested Time (in hours)
activity | topic | description | date | home
planning | rough planning | discussed the main goals and topics of the SSU | 2019-05-04 | 1.5
work | creation of the presentation of diploma thesis | structured the presentation and created the powerpoint presentation | 18 May 2019 | 2
work | presentation of diploma thesis | presented the diploma thesis to the appropriate professors | 2019-05-29 | 0.5
planning | work packages | divided the diploma thesis in work packages and assigned them appropriately | 2019-06-09 | 1
learning | online PHP course | preparing for the website programming by learning basics of PHP (syntax) | 2019-06-29 | 1
learning | online PHP course | continued on with PHP course (functions, arrays) | 2019-07-06 | 1
work | work on LED strip | cut and remove insulation from cables for LED strip | 2019-07-24 | 2
work | cut and grind parts to size | cut and grind some plastic inserts to size | 2019-07-24 | 1
work | polish the plastic inserts | Fabian and I polished the plastic inserts for the drawers | 2019-07-24 | 3
planning | website design | i designed the first website layout version | 2019-07-26 | 2
work | polish the plastic inserts | Fabian and I polished the plastic inserts for the drawers | 2019-07-27 | 2.25
work | polish the plastic inserts | Fabian and I polished the plastic inserts for the drawers | 2019-07-28 | 1.75
work | polish the plastic inserts | Fabian and I finished polishing the plastic inserts for the drawers | 2019-07-30 | 2.5
work | glue plastic inserts into drawers | Fabian and I started to glue the polished plastic inserts into the drawers of the small part storages | 2019-08-03 | 1.75
work | glue plastic inserts into drawers | Fabian and I finished to glue the polished plastic inserts into the drawers of the small part storages | 2019-08-04 | 1.25
learning | online PHP course | continued on with PHP course (html form handling, conditionals and logic) | 2019-08-03 | 1
work | micro controller wiring | soldered the ends of the flat cable | 2019-09-07 | 3
work | wooden framework | built in shelves in wooden framework | 2019-09-07 | 2.5
work | test LED strips | tested the functionality of the led-strips after inserting the storages into the wooden framework | 2019-09-07 | 1
meeting | test micro scale | tested and discussed the micro scale in the laboratory | 2019-09-09 | 0.75
work | test circuit board | tested circuit board, then improved it due to some resistors being too large | 2019-09-11 | 3
work | test LED strips | tested the LED strip, finalized installing in the storage unit | 2019-09-11 | 3
planning | diploma thesis database | we gathered information to fill the diploma thesis database | 2019-09-12 | 2
work | micro scale casing | completed the micro scale casing | 2019-09-15 | 2
work | built in micro scale | built in the micro scale into the storage unit | 2019-09-15 | 4
planning | project management deadlines | set deadlines for project management work packages | 2019-09-16 | 2
work | website HTML code | started coding the very rough overlay of the website in HTML | 2019-09-21 | 2
planning | rough project plan | made a rough project plan with up-to-date information | 2019-09-23 | 1.5
planning | diplma thesis database | restructured information for diplma thesis database after getting advice/corrections from coach | 2019-09-26 | 2
work | website CSS code | added the colours from our set colour pallet to some elements on the page | 2019-09-28 | 2
planning | project structure plan | we made a project strucure plan with all of the work packages in it | 2019-09-30 | 2
planning | diploma thesis database: final | submitting the final version of the diploma thesis database information | 2019-10-03 | 0.5
planning | gantt chart | transferred the work packages from psp to the teamgantt online tool and assigned to members | 2019-10-07 | 2
work | diploma thesis documentation | wrote a description of our starting situation | 2019-10-09 | 1.25
planning | restructure project structure plan | after getting feedback from our coach we restructured the psp | 2019-10-10 | 3
planning | gantt chart new work packages | I changed the work packages in the gantt chart according to the new psp | 2019-10-14 | 1
planning | entered dates for gantt chart | I estimated the times to start and complete each work package and entered the start and finish dates | 2019-10-17 | 3
planning | create dependencies in gantt chart | I connected certain work packages with dependencies to complete the gantt chart | 2019-10-21 | 2
work | website design | design the login and home page of the website | 2019-10-24 | 1.5
work | website design | design the search results page and page for adding/withdrawing items | 2019-10-28 | 2
work | website structure: login page | started structuring the login page of the website with HTML | 2019-11-07 | 2
work | website structure: login page | completed structuring the login page of the website with HTML | 2019-12-16 | 1
work | website structure: home page | started structuring the home page of the website with HTML | 2019-12-19 | 1
work | website structure: home page | completed structuring the home page of the website with HTML | 2019-12-20 | 3
work | website style: login page | wrote a stylesheet(CSS) file and applied it to the login page | 2019-12-21 | 7
work | website code: database connection | programmed a php script that connects the database to the website | 2019-12-22 | 1.5
work | website code: login script | programmed a php script for the login page that redirects a user to the home page and changes the state in the db | 2019-12-22 | 8.25
work | website style: general | wrote a generic stylesheet for all web pages (same outlines, header) | 2019-12-23 | 4
work | website style: home page | set CSS rules in a stylesheet specifically for the home page and applied it | 2019-12-23 | 4
work | website style: general | created a uniform header and footer as well as a container style for all pages apart from the login page | 2019-12-23 | 2.75
work | website code: logout script | wrote a small php script that logs a user out of the site and changes the state in the db | 2019-12-24 | 1
work | website code: checking if user logged in | created a detailed outline for a function that checks if a user is logged in without implementing it to all pages | 2019-12-24 | 5
work | website code: general | created error messages sent back by php scripts | 2019-12-24 | 2.5
work | website structure: manage profile page | structured the manage profile page of the website with all the inputs needed with HTML | 2019-12-25 | 2
work | website style: manage profile page | set CSS rules in a stylesheet specifically for the manage profile page and applied it | 2019-12-25 | 4
work | website code: manage profile page | started programming the php script that changes the profile data in the database | 2019-12-25 | 3
work | website code: manage profile page | continued programming the php script that changes the profile data in the database | 2019-12-26 | 7.75
work | website style: general add-ons | added some new styling (e.g. transitions) elements to existing pages | 2019-12-26 | 1.5
work | website code: general | created a php file with functions like hashPwd and other routines | 2019-12-27 | 0.5
work | website structure: results page | structured the results page of the website with HTML (very similiar to home page) and applied stylesheet | 2019-12-27 | 0.25
work | website code: general | went through every script and added extra checks for specific actions, also refactored parts of the code | 2019-12-28 | 3
work | website code: manage profile page | finished programming the php script that changes the profile data in the database. regarded all input cases/variants | 2019-12-28 | 7
learning | javascript event listeners | researched which event listeners in js I needed and in which way I could use them. exercised js syntax | 2019-12-29 | 5
work | website style: general | corrected and adjusted the generic header and footer for newly added elements | 2019-12-31 | 2.75
work | website code: home page | added 4 buttons with 4 different functionalities related to the items table | 2019-12-31 | 2
work | website code: home page | added the table of items from the db and bound it with the buttons | 2020-01-01 | 3.75
work | website code: home page | programmed the behaviour of the buttons when an item in the items table/list is selected | 2020-01-01 | 2.5
work | website structure: manage permissions page | structured the manage permissions page of the website and added a link to this page in all of other page headers | 2020-01-02 | 2.25
work | website code: manage permissions page | added an sql statement to the script to select the permissions of the respective user roles | 2020-01-02 | 0.75
work | website code: manage permissions page | wrote the php script that returned all changeable permissions and the current permission status | 2020-01-02 | 3
work | website style: manage permissions page | set CSS rules in a stylesheet specifically for the manage permissions page and applied it | 2020-01-03 | 4
work | website code: home page | wrote a script for reference of the clicked item in the table to allow access to its id in other pages (JavaScript) | 2020-02-05 | 2.5
work | website structure: withdraw item page | structured the withdraw item page of the website and prepared images of differently organized drawers for display | 2020-02-08 | 3
work | website structure: withdraw item quantity page | structured, styled and coded the page to select quantity of item to withdraw (item data also displayed on this page) | 2020-02-08 | 3.25
work | website style: withdraw item page | started setting CSS rules in a stylesheet specifically for the withdraw item page | 2020-02-09 | 2
work | website style: withdraw item page | continued styling the withdraw item page | 2020-02-10 | 4.25
work | website style: withdraw item page | finished styling the withdraw item page and applied the stylesheet | 2020-02-12 | 1
work | website code: withdraw item page | wrote the code for the page to get parts of the neccessary information (user color, permission) from the database | 2020-02-14 | 2.25
work | website code: withdraw item page | wrote the code to get all storage drawers containing selected item. tested multiple cases (differently organized drawers) | 2020-02-15 | 4
work | website code: withdraw item page | wrote a function that displays the correct drawer image with the area where the item is stored marked in the image | 2020-02-16 | 3.25
work | website code: withdraw item page | wrote a script that decides if there is more than one storage position and programmed the "next" button accordingly | 2020-02-17 | 4.75
work | website code: withdraw item page | wrote the code to display the correct amount of items to withdraw | 2020-02-18 | 4.25
work | website code: withdraw item page | wrote the code to update quantity/delete storage position in the database depending on the amount of items to withdraw | 2020-02-19 | 3.5
work | website code: withdraw item page | wrote the code that activates the blinking LED in the appropriate storageslot | 2020-02-23 | 4.25
work | website code: withdraw item page | wrote the code that activates the blinking LED in the appropriate storageslot | 2020-02-26 | 1
work | website structure: store page - item selection | structured the page where user selects the item being stored | 2020-02-26 | 1
work | website style: store page - item selection | set CSS rules in a stylesheet specifically for the store item - item selection page | 2020-02-26 | 2.5
work | website structure: store page - quantity input | structured the page where user puts in the quantity being stored | 2020-03-02 | 0.5
work | website style: store page - quantity selection | set CSS rules in a stylesheet specifically for the store item - quantity selection page | 2020-03-02 | 1
work | website structure: store page - slot selection | structured the page where user selects the storage slot the items will be stored in | 2020-03-05 | 0.5
work | website style: store page - slot selection | set CSS rules in a stylesheet specifically for the store item - slot selection page | 2020-03-05 | 0.75
work | website code: store page - item selection | filled the list with items to store and saved the chosen item after selection | 2020-03-05 | 0.25
work | website code: store page - quantity input | filled the item data list and set limits for the possible storing quantity | 2020-03-07 | 1
work | website code: store page - slot selection | wrote a statement that gets all storage slots from the database and filled the select element with them | 2020-03-07 | 1.5
work | website code: store page - slot selection | added an if condition that filters the slots that are in some way reserved or occupied | 2020-03-09 | 2.75
work | website structure: store page | structured the page where user puts in the necessary data for the database dataset to be created | 2020-03-12 | 1.25
work | website style: store page | set CSS rules in a stylesheet specifically for the store page | 2020-03-14 | 2
work | website code: store page | filled the inputs automatically if the chosen item has a reserved slot with enough space to store the chosen quantity | 2020-03-15 | 4.5
work | website code: store page | wrote the code to light up the LED and insert the dataset with the necessary item and slot data into the database | 2020-03-16 | 5.75
work | website general: micro scale functionality | programmed the micro scale interaction for withdrawing and storing processes | 2020-03-17 | 2.25
work | website structure: inventory report page | structured the page where user selects the type of inventory report to create and send | 2020-03-18 | 0.25
work | website style: inventory report page | set CSS rules in a stylesheet specifically for the inventory report page | 2020-03-18 | 0.25
work | website code: inventory report page | wrote the code that calls and executes the python script with the correct arguments | 2020-03-18 | 0.75
work | website general: testing and final fixes | implemented ready to go features, fixed minor/styling issues and uploaded onto the webserver | 2020-03-18 | 1
work | documentation: website - general | documented the general information about the website without going into the details of every page | 2020-03-20 | 3.25
work | documentation: website - general | documented the header and the footer (same for every page) | 2020-03-22 | 1.75
work | documentation: website - home page | documented the item list and the navigation of the home page and added "database connection" to the general part | 2020-03-23 | 3.75
work | documentation: website - withdraw pages | documented 1 of the 2 pages related to the withdrawing items function and started the second | 2020-03-24 | 1.5
work | documentation: website - withdraw pages | continued documenting the second page related to the withdrawing items function | 2020-03-26 | 0.5
work | documentation: milestones | documented the diploma thesis milestones | 2020-03-26 | 0.75
work | documentation: website - withdraw pages | finished documenting the second page related to the withdrawing items function | 2020-03-27 | 3.5
work | documentation: website - withdraw script | documented the withdraw script closing the withdrawing items chapter | 2020-03-28 | 0.75
work | documentation: meetings | documented the meetings with the coach surrounding the diploma thesis | 2020-03-28 | 0.5
work | documentation: diary | Transferred the diary (until this entry) into the documentation and adjusted the formatting | 2020-03-29 | 1
work | documentation: website - store pages | documented the item, quantity and storage slot selection for the store feature | 2020-04-06 | 3
work | documentation: website - store pages | documented the store page | 2020-04-07 | 1.5
work | documentation: website - store script | documented the store script finishing the store items part of the website | 2020-04-08 | 2
work | documentation: website - inventory report | documented the inventory report page and script of the website | 2020-04-09 | 0.75
work | documentation: website - user system | documented the profile management and the permissions page of the website | 2020-04-09 | 1
work | documentation: gantt chart | documented the gantt chart creation and the diagram itself | 2020-04-10 | 1.5
work | documentation: target-performance comparison | documented the deviation from the plan during the development of the project | 2020-04-10 | 3
work | documentation: abstract | written the abstract and translated it to german | 2020-04-11 | 3.5

## Timetable
work hours done: | 279