## Tabelle1
Date | Duration | Title | Description
04 May 2019 | 1:30 | Rough planning | We set our goals and discussed what the Smart Storage Unit should do
29 May 2019 | 2:00 | First Presentation | We made the first presentation
2019-06-09 | 0:30 | Gathering work packages | We gathered the necessary work packages and assigned them to the members
2019-06-09 | 2:45 | Design base components | I reproduced the small part storages in Fusion 360
2019-06-14 | 5:00 | Design inner frame | I designed the inner frame and how the small part storages are placed in them
2019-06-15 | 1:30 | Design outer frame | I designed the outer frame and the spacers between inner and outer frame
2019-07-24 | 5:00 | Polish plastic inserts | Rudolf and I polished the plastic inserts for the drawers
2019-07-25 | 4:30 | Design drawer for micro scale | I started the design of the drawer for the micro scale
2019-07-27 | 2:15 | Polish plastic inserts | Rudolf and I polished the plastic inserts for the drawers
2019-07-28 | 1:45 | Polish plastic inserts | Rudolf and I polished the plastic inserts for the drawers
2019-07-30 | 2:30 | Polish plastic inserts | Rudolf and I finished polishing the plastic inserts for the drawers
2019-07-31 | 3:15 | Redesign drawer for micro scale | I redesigned part of the drawer, due to its being too small for the micro scale
2019-08-03 | 1:45 | Glue plastic inserts into drawers | Rudolf and I started to glue the polished plastic inserts into the drawers of the small part storages
2019-08-04 | 1:15 | Glue plastic inserts into drawers | Rudolf and I finished to glue the polished plastic inserts into the drawers of the small part storages
2019-08-07 | 0:45 | Create rough database structure | I created the first database structure
2019-08-10 | 3:15 | Build wooden frame | I built the inner framework and cut the spacer into the right size
2019-08-11 | 2:30 | Build wooden frame | I built the outer framework and tried to fit the inner framework inside
2019-08-15 | 0:45 | Testing the touch panel | I connected and tested the touchscreen for functionality
2019-09-05 | 1:25 | Correct drawer for micro scale | I made few changes to the drawer to optimize the look of the 3d – print
2019-09-07 | 4:00 | Build small part storages into frame | We built the smart part storages into the inner frame and tested the LED – strips
2019-09-09 | 0:45 | Test and discuss micro scale in school’s laboratory | We tested and measured the microscale in the school’s laboratory
2019-09-09 | 4:45 | Solder circuit board | Stefan and I soldered the circuit board and built in the power supplies
2019-09-10 | 1:15 | Solder circuit board | Stefan and I finished the soldering, we also built in the 3d – printed drawer for the micro scale
2019-09-11 | 2:00 | Test and improve circuit board | We tested and improved the circuit board, due to some resistors being too large
2019-09-15 | 3:45 | Build micro scale into drawer | We built the micro scale and the servo motor into the drawer
2019-09-15 | 2:15 | Solder circuit board | We further improved the circuit so that there is also a port for the micro scale and the additional ADC
2019-09-18 | 2:15 | Testing I2C interface | I built and tested the I2C interface between the Arduino and the Raspberry Pi
2019-09-21 | 1:30 | Make rough project plan | We made a rough project plan
2019-09-22 | 0:45 | Adjust rough project plan | We adjusted some English phrases and words in the rough project plan
2019-09-26 | 2:00 | Make the project structure plan | We made a project structure plan with all of the work packages in it
2019-09-30 | 3:00 | Set up website | Stefan and I put up the https website, also we opened some ports so that public access is possible
05 Oct 2019 | 6:45 | Set up mail server | I set up an email-server so that the raspberry can send emails with an inventory report attached
05 Oct 2019 | 1:45 | Test and solder amplifier circuit | Due to the tiny output voltage of the micro scale Stefan and I built the amplifier circuit
22 Oct 2019 | 0:30 | Gathering ideas to improve the database | We tried to improve the database structure so that we can easily store information of items
24 Oct 2019 | 0:45 | Discuss and improve database | We and Prof. Frauscher talked about the database structure and a way how to save item data
24 Oct 2019 | 0:30 | Apply the gathered ideas | I applied the gathered ideas to the database structure
25 Oct 2019 | 2:45 | Set up database | I set up the database on the Raspberry Pi
26 Oct 2019 | 1:15 | Create test data | I created some test data for the database, in order to be able to test code
2019-11-11 | 4:15 | Code the Arduino program | I started coding the Arduino program for receiving I2C commands and setting the LED – strips
2019-11-16 | 1:45 | Code the Arduino program | I fixed the about the tick length of the LEDs
2019-11-18 | 0:15 | Installing PyQt5 on Raspberry Pi | I installed the python module “PyQt5” on the Raspberry for simplified designing of the GUI
2019-11-18 | 1:45 | Code the login screen | I started to code the login screen for the touch panel
2019-11-23 | 0:45 | Format the documentation | I formatted the documentation and inserted the main heading
2019-11-23 | 0:15 | Update project structure plan | I updated the plan to the current progress
2019-11-23 | 1:45 | Write the database documentation | I documented the tables and defined all the column names and their usages
05 Dec 2019 | 1:30 | Write the project management documentation | I documented project goals and the definition of task
23 Dec 2019 | 4:15 | Improve accuracy of micro scale | Stefan and I searched for accuracy problems of the micro scale and tried to fix them
23 Dec 2019 | 3:00 | Linearize the micro scale | Stefan and I set up a formula to convert the digital values of the micro scale into grams
23 Dec 2019 | 2:15 | Code the drawer controller | I coded a controller for the drawer and the measurement of the micro scale
24 Dec 2019 | 0:45 | Fix bugs of drawer controller | I fixed the bugs of the drawer controller
24 Dec 2019 | 0:45 | Code the login screen | I finished the login screen
25 Dec 2019 | 2:45 | Learn some basics of python and PyQt5 | I watched some videos and read through some website, in order to get the required knowledge for the next tasks
25 Dec 2019 | 2:15 | Design main, manage profile screen | I designed the main and manage profile screen
25 Dec 2019 | 3:30 | Connect login, main, manage profile screen | I coded a connection between login, main and manage profile screen
26 Dec 2019 | 2:45 | Create modules for database, i2c, servo and adc | I programmed modules (in python) for an easier connection and reuse of code
26 Dec 2019 | 0:45 | Add and modify tables | I added a new table to handle the active LEDs
26 Dec 2019 | 2:15 | Code the led controller | I added an LED controller to the drawer controller
27 Dec 2019 | 0:45 | Fixing bugs in led controller | I fixed some bugs in the LED and drawer controller
27 Dec 2019 | 1:30 | Inserting colour picker | I inserted a colour picker in the profile manager, so that everybody can choose the profile colour by his own
27 Dec 2019 | 2:45 | Outsource data handling | I wrote a class, in order to outsource the data filling of the main screen and create reusable code
27 Dec 2019 | 1:15 | Design permission and user screen | I designed the selection, add and change user/permission screen
27 Dec 2019 | 2:45 | Coding user and permission selection screen | I coded a screen, to whether select a user or permission
27 Dec 2019 | 1:30 | Coding add permission screen | I coded a form, that allows the user to add new roles to the database
28 Dec 2019 | 1:15 | Coding change permission screen | I coded a screen, in order to change permission of a role
28 Dec 2019 | 2:15 | Coding add user screen | I wrote a new screen, that can add new users to the system
28 Dec 2019 | 1:00 | Coding change user screen | I added a screen, in order to change the properties of a user like username, password and permission
28 Dec 2019 | 1:00 | Design selection screen for any kind of item selection | I designed a selection screen, which can be multiple used (for every item selection)
28 Dec 2019 | 0:45 | Coding possibility to delete | I added a button to the manage permission and manage user screen, so that it is possible to delete users and roles
28 Dec 2019 | 2:30 | Coding item selection screen | I coded the selection screen, in order to do I added another data handler class
29 Dec 2019 | 0:15 | Design the quantity selection screen | I made a screen that allows the user to type in the quantity to withdraw
29 Dec 2019 | 1:15 | Searched and fixed a bug | I searched and fixed a bug in the LED controller, which causes the controller to crash
29 Dec 2019 | 0:45 | Coding quantity selection screen | I coded the screen, which is used for selection the quantity of a withdrawing item
29 Dec 2019 | 1:45 | Coding module for better led/micro scale management | I outsourced the LED turn off and on functions to an extra module, I also added a function to extend and retract the micro scale
29 Dec 2019 | 0:30 | Design withdraw screen | I designed a screen, in order to withdraw item from the storage
29 Dec 2019 | 3:15 | Started coding of the withdraw screen | I started to code the withdrawing function of the storage, at first to turn on the led at the right place and then to switch between multiple storage slots
30 Dec 2019 | 0:30 | Optimize design of withdraw screen | I optimized the design of the item screen, due I forgot to leave an area for the micro scale controls to pop-up, if required
30 Dec 2019 | 1:15 | Changes to withdraw function | I had to make some heavy changes to the withdraw function, due to the new design
30 Dec 2019 | 4:30 | Continue coding of withdraw screen | I continue with the code of the withdraw screen
30 Dec 2019 | 1:30 | Searching improvements for micro scale | I searched online for possible ways to improve the micro scale and get rid of the oscillation
30 Dec 2019 | 0:15 | Apply improvements to micro scale | I applied the found improvements to the circuit (adding decoupling capacitor)
31 Dec 2019 | 5:45 | Rearranging the WiFi settings | Due to the new WiFi router and a new internet provider, the whole network settings had to be rearranged, so that a public access is possible again
31 Dec 2019 | 3:15 | Finishing withdraw item screen | I finished the withdraw item screen
01 Jan 2020 | 1:15 | Searching a module for the PDF creator | I searched for a python module, in order to create pdf with a Python program
01 Jan 2020 | 2:30 | Started coding the PDF creator | I started to code the PDF creator, I wrote a parse argument function and created the cover, header and footer
01 Jan 2020 | 0:30 | Rearranging the data handler | I made some changes to the data handler class, in order to select different datasets for the various tasks
01 Jan 2020 | 0:45 | Creating item selection for store function | I copied the selection screen from the withdraw function and made some changes, so that it can be used for the store function as well
01 Jan 2020 | 1:30 | Coding the item management screen | I added a management screen for items, so that new items can be added, and already existing ones can be edited
01 Jan 2020 | 0:45 | Design add/edit item screen | I designed a screen to add new items to the database
01 Jan 2020 | 3:30 | Code add item screen | I coded the add item screen, so that new items are saved in the database
02 Jan 2020 | 2:15 | Code PDF creator | I continue to code the PDF creator, I added HTMLMixin, in order to create tables inside the PDF
02 Jan 2020 | 2:15 | Code edit item screen | I coded a screen that allows users to change all properties of an item
02 Jan 2020 | 1:30 | Transfer the add/edit screen to the main screen | I transferred the button that opens the add/edit screen to the main screen
02 Jan 2020 | 0:30 | Search and fix bug in withdraw screen | I searched and fixed a bug in the withdraw screen (in some special situations dataset didn’t get deleted)
03 Jan 2020 | 3:15 | Code the send email function to the PDF creator | I coded the email function to the PDF creator, I also added a new argument to the program, in order to know the corresponding email address
03 Jan 2020 | 0:45 | Design set quantity screen | I copied the selection screen and the withdraw screen of the withdraw function and changed them, so that they fit for the set quantity function
03 Jan 2020 | 2:15 | Coding the set quantity screen | I coded the set quantity screen
03 Jan 2020 | 1:30 | Fixing bugs | I fixed some bugs in the manage profile, mange user and manage permission screen
04 Jan 2020 | 0:45 | Coding the monthly report program | I coded a program, which gathers all users and sends a inventory report to them
04 Jan 2020 | 0:15 | Setting the crontab | In order to send a report on the 1st of every month, I set the monthly report program in a crontab
04 Jan 2020 | 1:15 | Changing the item quantity selection screen | I applied some changes to the item quantity screen, so that it can be also used for the store function
05 Jan 2020 | 2:30 | Changing the pdf orientation | I swapped the orientation of the sheet in the PDF creator to landscape
05 Jan 2020 | 0:45 | Testing the functions | I tested nearly every function, in order to find existing bugs
18 Jan 2020 | 2:15 | Designing screens for the store function | I designed multiple screen for the store function
19 Jan 2020 | 3:30 | Coding the store function | I started to code the store function, the screen to select an item and set the quantity work
19 Jan 2020 | 0:30 | Designing the create inventory report screen | I designed the create inventory screen
19 Jan 2020 | 1:30 | Coding the create inventory report screen | I coded the screen, which starts the PDF creator
25 Jan 2020 | 2:00 | Fixing bugs | I fixed the bugs, which were discovered on the open day of the school
26 Jan 2020 | 1:30 | Changing screen designs | I change multiple screen designs, due Prof. Frauscher mentioned that it is a bit confusing
2020-02-01 | 0:45 | Explaining functions | Stefan explained me the process flow of his store function so we that we have the same process flow
2020-02-01 | 1:15 | Changing designs of the store screens | Due to Stefan process flow, I had to make some changes to my store screens
2020-02-02 | 2:25 | Add storage management functions | I added functions to delete and move the storage slots
2020-02-03 | 1:30 | Coding the store function | I continued with the store function and added the save
2020-02-13 | 1:15 | Recreating the word document | I recreated the word document of the diploma thesis, the reason for this are the tricks and management ideas Prof. Dusleag gave us in his presentation
2020-02-13 | 1:30 | Correcting the documentation | I corrected the documentation, after I found some mistakes in the writing
2020-02-16 | 3:30 | Write documentation | I wrote about some parts of the project management, I also rewrote the database documentation, due it was outdated
2020-02-17 | 3:15 | Write documentation | I described the basic of the Arduino and how it is integrated into the project
2020-02-18 | 2:30 | Write documentation | I described the Raspberry Pi and the database
2020-02-19 | 1:45 | Write documentation | I described my LED-Manager program for the Arduino
2020-02-20 | 2:00 | Write documentation | I described the database executer, which activates the LEDs and the servo motor
2020-02-21 | 2:45 | Write documentation | I described the PDF creator and how the emails are sent
2020-02-22 | 1:30 | Write documentation | I described the monthly report sender and made some changes to my written documentations
2020-02-27 | 1:15 | Fixing bugs | I fixed some bugs which were discovered during the “Jobtech” event
17 Mar 2020 | 0:30 | Write documentation | I had to rewrite some passages, due to the fixed bugs
19 Mar 2020 | 1:15 | Write documentation | I documented the basics of the touch panel as well as PyQt5
20 Mar 2020 | 1:45 | Write documentation | I described the main menu and how it works
22 Mar 2020 | 0:45 | Write documentation | I documented the create inventory screen
26 Mar 2020 | 0:30 | Write documentation | I documented how the colours of the LED – strips are set
27 Mar 2020 | 1:30 | Write documentation | I documented the storage management of the touch panel
28 Mar 2020 | 2:15 | Write documentation | I documented the item and user management of the touch panel
31 Mar 2020 | 1:15 | Write documentation | I pasted my project diary into the document
2020-04-01 | 0:45 | Write documentation | I added all the required code snippets and figure to the document
2020-04-03 | 0:30 | Write documentation | I started describing the withdraw function
2020-04-04 | 1:15 | Write documentation | I continued to describe the withdraw function
2020-04-05 | 0:45 | Write documentation | I finished the withdraw function and started to describe the store function
2020-04-08 | 1:15 | Write documentation | I continued to describe the store function
2020-04-09 | 0:30 | Write documentation | I finished to describe the store function
Total: | 251:45