## Diary
Diploma thesis diary: |  |  |  | 5BHET
Stefan Zauper |  |  |  | 2019/20
| Time worked (in hours): | 278.9 | Invested Time (in hours)
activity | topic | date | home | school
planning | rough planning | 2019-05-04 | 1.5
work | presentation of diploma thesis | 2019-05-29 | 2
planning | work packages | 2019-06-09 | 0.5
work | buy/order components/material | 2019-07-20 | 2
work | solder LED strips | 2019-07-24 | 4
work | solder LED strips | 2019-07-27 | 6
work | built LED strips in big shelve | 2019-07-28 | 2
work | solder LED strips | 2019-07-29 | 4
work | solder LED strips | 2019-08-03 | 2
work | built LED strips in big shelve | 2019-08-03 | 2
work | solder LED strips | 2019-08-04 | 3
work | tested finished shelves | 2019-08-09 | 3
work | solder LED strips | 2019-08-10 | 3
work | built LED strips in big shelve | 2019-08-11 | 2
work | solder LED strips | 2019-08-17 | 3
work | built LED strips in small shelve | 2019-08-18 | 1
work | solder LED strips | 2019-08-24 | 3
work | built LED strips in small shelve | 2019-08-25 | 1
work | built in shelves in wooden framework | 2019-09-07 | 4
work | test LED strips | 2019-09-07 | 0.5
work | solder circuit board to be pluggable | 2019-09-07 | 2
meeting | test and discuss the micro scale in the schools laboratory | 2019-09-09 | 0.75
work | solder circuit board and cables to be pluggable | 2019-09-09 | 5
work | solder circuit board and cables to be pluggable | 2019-09-10 | 1
work | test circuit board | 2019-09-11 | 2
work | built in micro scale | 2019-09-15 | 4
work | solder circuit board and cables to be pluggable | 2019-09-15 | 2
work | setup raspberry pi/setup wifi/enabled SSH and I2C | 2019-09-17 | 3
work | setup openVPN | 2019-09-21 | 3.5
planning | PSP-plan | 2019-09-26 | 2
work | setup https on raspberry | 2019-09-30 | 3
work | solder amplifier circuit | 2019-10-05 | 8
planning | finalize Gantt chart | 2019-10-07 | 2
meeting | talk about project management with teacher | 2019-10-10 |  | 2
work | design layout for login screen | 2019-10-21 | 2
work | design layout for login and overview screen | 2019-10-28 | 2
work | design layout for overview screen | 2019-10-30 | 1.5
work | code overview screen | 2019-11-04 | 4
presentation | read AC/DC converter values over bus | 2019-11-11 |  | 2
presentation | µC design layout with eagle | 2019-11-14 |  | 2
presentation | smart meter | 2019-11-18 |  | 2
presentation | webserver with PLC | 2019-11-21 |  | 2
work | code overview screen | 2019-11-25 | 2
work | code overview screen | 2019-11-26 | 2.5
presentation | webserver with PLC | 2019-11-28 |  | 2
work | code login screen | 2019-12-01 | 3
presentation | presentation of all diploma thesises | 2019-12-02 |  | 1.2
work | code login screen | 2019-12-02 | 1
work | improved accuracy of micro scale | 2019-12-23 | 7.25
work | code login screen (db-connector) | 2019-12-26 | 7.75
work | code login screen (db-connector) | 2019-12-27 | 9.75
work | code overview screen | 2019-12-28 | 10
work | code store item screen | 2019-12-29 | 11
work | fixed bugs | 2019-12-30 | 8
work | code store item screen | 2019-12-31 | 6
work | code store item screen | 2020-01-01 | 5
work | code store item screen | 2020-01-02 | 9
work | code store item screen | 2020-01-03 | 7
work | code store item screen | 2020-01-04 | 10
work | code withdraw screen | 2020-01-07 | 4.15
work | code withdraw screen | 2020-01-08 | 5
work | code overview screen | 2020-01-12 | 8
work | code settings screen | 2020-02-01 | 6
work | code withdraw screen | 2020-02-04 | 7
work | code correct quantity screen | 2020-02-08 | 6
work | code delete storage slot screen | 2020-02-10 | 7
work | code to make a report from the ssu | 2020-02-24 | 4
work | writing diploma thesis | 2020-03-16 | 3
work | writing diploma thesis | 2020-03-17 | 3
work | writing diploma thesis | 2020-03-18 | 2
work | writing diploma thesis | 2020-03-19 | 1.5
work | writing diploma thesis | 2020-03-20 | 3
work | writing diploma thesis | 2020-03-21 | 1
work | writing diploma thesis | 2020-03-22 | 2
work | writing diploma thesis | 2020-03-23 | 2.5
work | writing diploma thesis | 2020-04-02 | 1.5
work | writing diploma thesis | 2020-04-03 | 3
work | writing diploma thesis | 2020-04-04 | 2.5
work | writing diploma thesis | 2020-04-05 | 2
work | writing diploma thesis | 2020-04-06 | 2
work | writing diploma thesis | 2020-04-07 | 0.5
work | writing diploma thesis | 2020-04-08 | 0.75
work | writing diploma thesis | 2020-04-09 | 0.5
work | writing diploma thesis | 2020-04-10 | 2
work | writing diploma thesis | 2020-04-10 | 2.5

## Timetable
work hours done: | 196.5